## Project tasks
Project name | AutumnDatabaseProject - Copy
Project manager | Praise Ojofeitimi
Project start date | 2024-08-22
Project finish date | 2024-09-13 17:00
Duration | 96 days
% complete | 100%
Exported on | 2024-08-26 08:08
Task number | Outline number | Name | Assigned to | Start | Finish | Duration | Bucket | % complete | Priority | Depends on | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Sprint | Goal
1 | 1 | Phase 1 |  | 2024-05-03 09:00 | 2024-08-09 17:00 | 71 days |  | 0% | Medium |  |  | 48 hours | 0 hours | 48 hours | No
2 | 1.1 | Project Decision |  | 2024-05-03 09:00 | 2024-05-03 17:00 | 1 day | Bucket 1 | 0% | Medium |  |  | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
3 | 1.2 | create project setup in intelllij |  | 2024-05-23 09:00 | 2024-05-23 17:00 | 1 day | Bucket 1 | 0% | Medium | 9FS, 4FS |  | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
4 | 1.3 | install all necessary applications |  | 2024-05-07 09:00 | 2024-05-07 17:00 | 1 day | Bucket 1 | 0% | Medium |  | 3FS | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
5 | 1.4 | research and investigans into jdbc |  | 2024-05-08 09:00 | 2024-05-09 17:00 | 2 days | Bucket 1 | 0% | Medium |  |  | 16 hours | 0 hours | 16 hours | No |  |  |  |  | Backlog
6 | 1.5 | finalise project idea |  | 2024-08-09 09:00 | 2024-08-09 17:00 | 1 day | Bucket 1 | 0% | Medium |  |  | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
7 | 2 | Phase 2 |  | 2024-05-10 09:00 | 2024-05-22 17:00 | 9 days |  | 0% | Medium |  |  | 120 hours | 0 hours | 120 hours | No
8 | 2.1 | Start Database Creation |  | 2024-05-10 09:00 | 2024-05-13 17:00 | 2 days | Bucket 1 | 0% | Medium |  | 9FS, 23FS, 24FS | 16 hours | 0 hours | 16 hours | No |  |  |  |  | Backlog
9 | 2.2 | Create Database and Tables |  | 2024-05-14 09:00 | 2024-05-22 17:00 | 7 days | Bucket 1 | 0% | Medium | 8FS | 3FS, 13FS | 56 hours | 0 hours | 56 hours | No |  |  |  |  | Backlog
10 | 2.3 | Tables Instrument, Rents, Wind, Percussion, Strings |  | 2024-05-15 09:00 | 2024-05-21 17:00 | 5 days | Bucket 1 | 0% | Medium |  | 11FS | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Backlog
11 | 2.4 | Test Functionality |  | 2024-05-22 09:00 | 2024-05-22 17:00 | 1 day | Bucket 1 | 0% | Medium | 10FS |  | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
12 | 3 | Phase 3 |  | 2024-07-16 09:00 | 2024-08-08 17:00 | 18 days |  | 0% | Medium |  |  | 144 hours | 0 hours | 144 hours | No
13 | 3.1 | Connect Database to Intellij |  | 2024-07-16 09:00 | 2024-07-16 17:00 | 1 day | Bucket 1 | 0% | Medium | 9FS | 18FS | 8 hours | 0 hours | 8 hours | No |  |  |  |  | Backlog
14 | 3.2 | Test functionality |  | 2024-07-16 09:00 | 2024-07-22 17:00 | 5 days | Bucket 1 | 0% | Medium |  |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Backlog
15 | 3.3 | Create classes for Project |  | 2024-07-29 09:00 | 2024-08-02 17:00 | 5 days | Bucket 1 | 0% | Medium |  | 16FS | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Backlog
16 | 3.4 | Populate classess |  | 2024-08-05 09:00 | 2024-08-07 17:00 | 3 days | Bucket 1 | 0% | Medium | 15FS |  | 24 hours | 0 hours | 24 hours | No |  |  |  |  | Backlog
17 | 3.5 | Test Functionally Fix any potential errors |  | 2024-08-06 09:00 | 2024-08-07 17:00 | 2 days | Bucket 1 | 0% | Medium |  |  | 16 hours | 0 hours | 16 hours | No |  |  |  |  | Backlog
18 | 3.6 | Create Test case for Database Connections |  | 2024-08-07 09:00 | 2024-08-08 17:00 | 2 days | Bucket 1 | 0% | Medium | 13FS |  | 16 hours | 0 hours | 16 hours | No |  |  |  |  | Backlog
19 | 4 | Phase 4 |  | 2024-08-19 09:00 | 2024-09-13 17:00 | 20 days |  | 0% | Medium |  |  | 560 hours | 0 hours | 560 hours | No
20 | 4.1 | Create video |  | 2024-09-02 09:00 | 2024-09-13 17:00 | 10 days | Bucket 1 | 0% | Medium | 21FS |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
21 | 4.2 | Create powerpoint slides |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium |  | 20FS | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
22 | 4.3 | Prepare link to GitHub |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium |  |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
23 | 4.4 | Microsoft Project File |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium | 8FS |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
24 | 4.5 | SQL Database file |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium | 8FS |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
25 | 4.6 | Write Essay |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium |  |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog
26 | 4.7 | Prepare Lab portfolio |  | 2024-08-19 09:00 | 2024-08-30 17:00 | 10 days | Bucket 1 | 0% | Medium |  |  | 80 hours | 0 hours | 80 hours | No |  |  |  |  | Backlog